## Slide 1: Agile Software development
- POOJA SUNDAR

## Slide 2: What is agile ?
Agile software development refers to a group of software development methodologies based on iterative development, where requirements and solutions evolve through collaboration between self-organizing cross-functional teams.

## Slide 3: Why we are using agile ?
Reduces Technical Debt
Easily and Quickly Adapt to Change
Using Agile for Mobile Application Development and Testing Creates Total Alignment and Transparency
Agile Software Development and Test Minimize Risk
Higher Quality Product

## Slide 4: Life cycle of sdlc (Software Development Life Cycle)
Stage 1 : Requirement collection and analysis
Stage 2 : Feasibility study
Stage 3 : Designing the Product Architecture
Stage 4 : Building or Developing the Product
Stage 5 : Testing the Product
Stage 6 : Deployment in the Market and Maintenance

## Slide 5: Waterfall methodology
Requirements Analysis
System Design
a) High-level design phase
b) Low-level design phase
Implementation
Testing
Deployment
Maintenance

## Slide 6: What is scrum ?
Scrum is a framework that helps teams work together. Often thought of as an agile project management framework, scrum describes a set of meetings, tools, and roles that work in concert to help teams structure and manage their work.

## Slide 7: A beginner’s guide to scrum ceremonies
Sprint Planning
Daily Scrum (Scrum Meeting)
Sprint Grooming
Sprint Review
Sprint Retrospective

## Slide 8: similarities between Agile and Waterfall methodologies :-
Agile model follows the incremental approach, after the iteration through every given time.
Customer interaction is very high.
After every process , Incrementation of the project is deployed to the client.
Agile model is not suitable model for small projects.
Waterfall methodology
Waterfall model follows a sequential design process.​
​Customer interaction is very low.
The product is delivered to the customer after overall development.
Waterfall model is not suitable for developing the large projects.
agile methodology

## Slide 9
Agile methodology
Its more Flexible. Also changes the requirement even after starting the development process.
The Test plan is reviewed after each sprint.
Waterfall methodology
Its more Rigid. We cannot change requirement once development process Started.
The Test plan is reviewed after full completion.

## Slide 10: advantages of Agile methodology :-
Client satisfaction is rapid, continuous development and delivery of useful software.
Client, Developer, and Product Owner interact regularly to emphasize rather than processes and tools.
Product is developed fast and frequently delivered (weeks rather than months.)
A face-to-face conversation is the best form of communication.
Daily and close co-operation between business people and developers.
Regular adaptation to changing circumstances.

## Slide 11: Disadvantages of Agile methodology :-
It is not useful for small development projects.
There is a lack of intensity on necessary designing and documentation.
It requires an expert project member to take crucial decisions in the meeting.
Cost of Agile development methodology is slightly more as compared to other development methodology.
The project can quickly go out off track if the project manager is not clear about requirements and what outcome he/she wants.

## Slide 12: Similarities between agile and scrum ?
Agile methodologt :-
Agile is a Development Methodology, based on incremental Approach.
In the Agile process, the leadership plays a vital role.
There is not much room for frequent changes .It is rigid method.
Scrum in agile :-
Scrum is one of the implementations of agile methodology .Incremental builds is delivered to clients within two to three weeks.
Scrum helps in self-organizing and cross-functional team.
It’s more flexible , and adapts to quick change.

## Slide 13
ANY QUERIES ???